## Project Planner
Project Planner: AGV-Project
| Plan Duration |  | Actual Start |  | % Complete |  | Actual (beyond plan) |  | % Complete (beyond plan)
ACTIVITY | ASSIGNED TO | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-28 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Hardware Diagram | Jordi | 1 | 1 | 1 |  | 100%
Gantt Diagram | Jordi | 1 | 1 | 1 | 1 | 100%
Class Diagram | Flemming | 1 | 1 | 1 |  | 100%
Communication Diagram | Rasmus | 1 | 1 | 1 |  | 100%
Simulation research | All | 1 | 4 | 1 |  | 0%
Control algorithms research | All | 2 | 2 |  |  | 0%
Path planning algorithms research | All | 2 | 2 |  |  | 0%
Task planning algorithms research | All | 2 | 2 |  |  | 0%
Make report algorithms | All | 2 | 2 |  |  | 0%
Hardware Assembly | All | 4 | 1 |  |  | 0%
RPI3 - Arduino Communication Test | All | 4 | 2 |  |  | 0%
Arduino - Motors Test | All | 4 | 2 |  |  | 0%
Arduino - Encoders Test | All | 4 | 2 |  |  | 0%
RPI3 - VICON Test | All | 4 | 2 |  |  | 0%
Testing Report | All | 4 | 2 |  |  | 0%
Mapping | All | 6 | 1 |  |  | 0%
Make robot do a route (Routing) | All | 6 | 3 |  |  | 0%
Path planning algorithms | All | 6 | 3 |  |  | 0%
Task planning algorithms | All | 6 | 3 |  |  | 0%
Report of all the tests done | All | 6 | 4 |  |  | 0%
Final prototype integration | All | 10 | 1 |  |  | 0%
Last validation tests | All | 11 | 2 |  |  | 0%
Write final report | All | 10 | 3 |  |  | 0%